## Sheet1
BURNDOWN CHART
| TASK TITLE | AMOUNT OF WORK IN HOURS |  |  | SPRINT
|  | ESTIMATED | COMPLETED | REMAINING
| Requirements Definition and Analysis | 34 | 34 | 0 | 1
| Requirements definition | 8 | 8 | 0 | 1
| User stories definition | 10 | 10 | 0 | 1
| Mock up | 8 | 8 | 0 | 1
| Architecture definition | 8 | 8 | 0 | 1
| Authentication Service Development | 39 | 39 | 0 | 2
| DB configuration for Users | 6 | 3 | 0 | 2
| Login backend implementation | 12 | 12 | 0 | 2
| Login and Registration pages | 8 | 7 | 0 | 2
| Admin Panel page – User Management Section | 8 | 7 | 0 | 2
| Bug Identification and Resolution | 5 | 10 | 0 | 2
| Monster Service Development | 31 | 31 | 0 | 3
| DB configuration for Monsters | 6 | 3 | 0 | 3
| Backend implementation | 12 | 13 | 0 | 3
| Admin Panel page – Monster Management Section | 8 | 8 | 0 | 3
| Bug Identification and Resolution | 5 | 7 | 0 | 3
| Item Service Development | 31 | 31 | 0 | 4
| DB configuration for Items | 6 | 3 | 0 | 4
| Backend implementation | 12 | 13 | 0 | 4
| Admin Panel page – Monster Management Section | 8 | 7 | 0 | 4
| Bug Identification and Resolution | 5 | 8 | 0 | 4
| Game Service Inizialization | 45 | 45 | 0 | 5
| DB configuration for Encounters | 6 | 3 | 0 | 5
| Partial game microservice implementation | 12 | 12 | 0 | 5
| Implementation of Inter-Service Communication | 6 | 8 | 0 | 5
| Home page | 8 | 8 | 0 | 5
| Encounter page | 8 | 8 | 0 | 5
| Bug Identification and Resolution | 5 | 6 | 0 | 5
| Game Service Development (Collection) | 31 | 31 | 0 | 6
| DB configuration for Collection | 6 | 3 | 0 | 6
| Extending game miscroservice (monster collection) | 12 | 10 | 0 | 6
| Collection page | 8 | 10 | 0 | 6
| Bug Identification and Resolution | 5 | 8 | 0 | 6
| Game Service Development (Invetory) | 39 | 39 | 0 | 7
| DB configuration for Inventory | 6 | 3 | 0 | 7
| Extending game miscroservice (inventory) | 12 | 14 | 0 | 7
| Shop page | 8 | 7 | 0 | 7
| Inventory page | 8 | 7 | 0 | 7
| Bug Identification and Resolution | 5 | 8 | 0 | 7
| Game Service Development (Statistics) | 31 | 31 | 0 | 8
| DB configuration for Statistics | 6 | 3 | 0 | 8
| Extending game miscroservice (Statistics) | 12 | 14 | 0 | 8
| Statistics page | 8 | 9 | 0 | 8
| Bug Identification and Resolution | 5 | 5 | 0 | 8
|  | ESTIMATED | COMPLETED | REMAINING | DAYS | EST/DAYS
| TOTAL HOURS | 281 | 281 | 0 | 56 | 5.0179
[8 empty] | SPRINT 1 | [6 empty] | SPRINT 2 | [6 empty] | SPRINT 3 | [6 empty] | SPRINT 4 | [6 empty] | SPRINT 5 | [6 empty] | SPRINT 6 | [6 empty] | SPRINT 7 | [6 empty] | SPRINT 8
[7 empty] | DAY | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
[7 empty] | PLAN | 281 | 275.9821 | 270.9643 | 265.9464 | 260.9286 | 255.9107 | 250.8929 | 245.875 | 240.8571 | 235.8393 | 230.8214 | 225.8036 | 220.7857 | 215.7679 | 210.75 | 205.7321 | 200.7143 | 195.6964 | 190.6786 | 185.6607 | 180.6429 | 175.625 | 170.6071 | 165.5893 | 160.5714 | 155.5536 | 150.5357 | 145.5179 | 140.5 | 135.4821 | 130.4643 | 125.4464 | 120.4286 | 115.4107 | 110.3929 | 105.375 | 100.3571 | 95.3393 | 90.3214 | 85.3036 | 80.2857 | 75.2679 | 70.25 | 65.2321 | 60.2143 | 55.1964 | 50.1786 | 45.1607 | 40.1429 | 35.125 | 30.1071 | 25.0893 | 20.0714 | 15.0536 | 10.0357 | 5.0179 | 0
[7 empty] | HRS COMPLETED | 5 | 5 | 4 | 4 | 5 | 5 | 6 | 8 | 8 | 13 | 4 | 3 | 3 | 0 | 8 | 8 | 4 | 4 | 4 | 3 | 0 | 8 | 8 | 4 | 4 | 4 | 3 | 0 | 8 | 8 | 8 | 6 | 5 | 5 | 5 | 7 | 6 | 5 | 5 | 4 | 4 | 0 | 6 | 6 | 5 | 7 | 7 | 4 | 4 | 7 | 6 | 5 | 5 | 4 | 4 | 0 | 0
[7 empty] | HRS REMAINING | 276 | 271 | 267 | 263 | 258 | 253 | 247 | 239 | 231 | 218 | 214 | 211 | 208 | 208 | 200 | 192 | 188 | 184 | 180 | 177 | 177 | 169 | 161 | 157 | 153 | 149 | 146 | 146 | 138 | 130 | 122 | 116 | 111 | 106 | 101 | 94 | 88 | 83 | 78 | 74 | 70 | 70 | 64 | 58 | 53 | 46 | 39 | 35 | 31 | 24 | 18 | 13 | 8 | 4 | 0 | 0 | 0
[14 empty] | 34 | [6 empty] | 39 | [6 empty] | 31 | [6 empty] | 31 | [6 empty] | 45 | [6 empty] | 31 | [6 empty] | 39 | [7 empty] | 31